Comprehensive Educational Plan (CEP) Assessment Scorecard

Development Process and Timeline

Phase 1: KPI Framework Development     September – December 2026

| Oct - Nov 2026 ¦ IR Office Develop KPI Framework • Review CEP goals and objectives. • Identify key construct(s) for each objective. • Develop KPIs for each construct. • Add operational definitions Initial KPI framework completed by October 31, 2026 | → | November 2026 ¦ Data Committee Vet and Refine • Review constructs, KPIs, and operational definitions. • Provide technical, contextual, end-user, and subject-matter feedback. • IR Office revises the draft based on feedback. Revised draft completed by November 30, 2026 | → | December 2026 ¦ IE&A Committee Review and Approve • Review revised KPI framework for alignment with the CEP, institutional priorities, and integrated planning. • Approve the measurement framework. KPI framework approved by end of Fall 2026 |
| --- | --- | --- | --- | --- |

Phase 2: Data, trends, and benchmarking 	January – May 2027

| Jan–Mar 2027 ¦ IR Office Collect, Analyze, and Recommend • Collect and validate data for each KPI. • Provide a one-year snapshot using the latest academic-year data. • Provide multi-year tracking to show trends. • Analyze results and develop recommended benchmarking methodology for each KPI. Benchmarking recommendations completed by March 31, 2027 | → | April 2027 ¦ Data Committee Review Benchmarks • Review actual measures, trends, and proposed benchmarking methods. • Provide technical, contextual, end-user, and subject-matter feedback. • IR Office revises recommendations based on feedback. Feedback and revisions completed by April 30, 2027 | → | May 2027 ¦ IE&A Committee Final Approval • Review and approve the complete scorecard framework. • Confirm KPIs and operational definitions. • Review actual measures and multi-year trends. • Approve benchmarking methodology. Approved by May 31, 2027 |
| --- | --- | --- | --- | --- |

Phase 3: Update and launch     Summer – Beginning of Fall 2027

| Summer 2027 ¦ IR Office Update and Finalize • Add newly available 2026–2027 academic-year data. • Validate measures and trends. • Finalize the scorecard for publication. | → | Beginning OF FALL 2027 Publish CEP Assessment Scorecard • Launch the finalized scorecard. • Share with the college community. • Use results to inform institutional planning, resource allocation, and ongoing assessment. |
| --- | --- | --- |

Santa Ana College Office of Research, Institutional Effectiveness & Planning